## Instructions & Notes
Go Live Plan
Client Name / Project Name / Implementation Designation
Participant Instructions
 No task may begin until its predecessor is completed... no jumping ahead in the timeline.
 Real-time progress can be obtained by 1) joining the Go Live Vitual Room or 2) joining the Go Live Phone Conference
 Task completion should be reported by 1) chat in the Go Live Virtual Room or 2) joining the Go Live Vitual Room and chatting there
 Difficulties, issues, and/or delays should be reported by 1) joining the Go Live Phone Conference or 2) calling the Go Live Manager on duty

Go Live Virtual Room
| Participant Link: | {link to Zoom, Skype, Teams, Hangouts, etc.}
Go Live Phone Conference
US Toll Free:
Access Code:
Reference Info
This area might include anything that the Go Live team would need at a moment's notice.
In this area, we have documented things like server names, database names, software versions, important URLs,
full path of folders containing additional important information, and other.
Workbook Content
| Tab | Description
| Instructions & Notes | This tab
| Timeline | The complete timeline of Go Live tasks
| Milestone Comms | The email distribution list for milestone completion communications
| App Checkout Issues | An issue log to track issues found during application checkout
| Contacts List | All participants in this Go Live effort
| Rollback Plan | The timeline of tasks to complete in case of a rollback (return to previous Production state)
| Author Instructions | Instructions for the creator and keeper of this workbook

## Timeline
| Planned |  |  | Actual
Task Nbr | Start Date Time | Duration | End Date Time | Start Date Time | Duration | End Date Time | Status | Responsibility | Activity | Comments
[9 empty] | Milestones are indicated like this, shaded in green. | Communications for milestones are to be communicated to the list on the "Milestone Comms" tab, unless otherwise noted.
"Handshakes" where this Go Live activity needs to wait for an external task are indicated like this, shaded in orange.
All times are in US Central time zone
| 2022-04-29 18:00 | [7 empty] | {{ Start Date-Time Place Holder }}
Pre Go Live Tasks
0.05 |  |  | 2022-04-14 |  |  |  |  | Jane D | Submit production change request
0.1 |  |  | 2022-04-15 |  |  |  |  | Jane D | Obtain production change request
0.15 |  |  | 2022-04-18 |  |  |  |  | John C | Send end user communications
0.2
0.25
0.9 | 2022-04-28 18:00 | 0:00 | 2022-04-28 18:00 |  |  |  |  | Change Advisory Board | Go/No Go to start Go Live
0.95 | 2022-04-29 17:46 | 0:00 | 2022-04-29 17:46 |  |  |  |  | James H | Open Go Live Phone Conference and Virtual Room
Go Live Tasks
1 | 2022-04-29 18:00 |  | 2022-04-29 18:00 | [5 empty] | Milestone: Go Live Start, Begin PROD Shutdown
1.1 | 2022-04-29 18:00 |  | 2022-04-29 18:00 |  |  |  |  | Business User Leadership | Stop end user use
1.2 | 2022-04-29 18:00 | 4:30 | 2022-04-29 22:30 |  |  |  |  | Mary H | Shutdown Tier 1: app a, system b, process c
1.4 | 2022-04-29 22:30 |  | 2022-04-29 22:30 |  |  |  |  | Tom T | Wait for external systems shutdown
1.6 | 2022-04-29 22:30 | 2:00 | 2022-04-30 00:30 |  |  |  |  | Mary H | Shutdown Tier 2: app x, system y, process z
8 | 2022-04-30 00:30 |  | 2022-04-30 00:30 | [5 empty] | Milestone: PROD Shutdown Complete
10 | 2022-04-30 00:30 |  | 2022-04-30 00:30 | [5 empty] | Milestone: Begin Data Migration
12 | 2022-04-30 00:30 | 1:30 | 2022-04-30 02:00 |  |  |  |  | Caleb J | Final data conversion/migration prep
14 | 2022-04-30 02:00 | 2:30 | 2022-04-30 04:30 |  |  |  |  | Ryan C | Data Conversion/Migration Process
16 | 2022-04-30 04:30 | 1:00 | 2022-04-30 05:30 |  |  |  |  | Claire D, Bill B | Validate data
16.5 | 2022-04-30 05:30 |  | 2022-04-30 09:00 | [5 empty] | Team Rest Break
18 | 2022-04-30 09:00 | 1:00 | 2022-04-30 10:00 |  |  |  |  | Ryan C | Data correction, if needed
20 | 2022-04-30 10:00 |  | 2022-04-30 10:00 | [5 empty] | Milestone: Data Migration Complete
30 | 2022-04-30 10:00 |  | 2022-04-30 10:00 | [5 empty] | Milestone: Being Applications Install
32 | 2022-04-30 10:00 | 1:30 | 2022-04-30 11:30 |  |  |  |  | Ryan C, Justin H | Install and Configure Applications A, B, C | Validate versions against those on Instructions & Notes tab
34 | 2022-04-30 11:30 | 1:00 | 2022-04-30 12:30 |  |  |  |  | Tammy K | Validate application install | Validate versions against those on Instructions & Notes tab
36 | 2022-04-30 12:30 | 1:00 | 2022-04-30 13:30 |  |  |  |  | Mary G | Setup user access | Reference User Access spreadsheet in project folder
38 | 2022-04-30 13:30 | 1:00 | 2022-04-30 14:30 |  |  |  |  | Tammy K, Bill B | Verify user access
40 | 2022-04-30 14:30 | 1:00 | 2022-04-30 15:30 |  |  |  |  | Tammy K, Bill B | Verify user access
42 | 2022-04-30 15:30 |  | 2022-04-30 15:30 | [5 empty] | Milestone: Applications Install Complete
50 | 2022-04-30 15:30 |  | 2022-04-30 15:30 | [5 empty] | Milestone: Begin Applications Verification
52 | 2022-04-30 15:30 | 1:00 | 2022-04-30 16:30 |  |  |  |  | Ryan C, Justin H | Tech Team Application Checkout
54 | 2022-04-30 16:30 | 1:30 | 2022-04-30 18:00 |  |  |  |  | Tammy K, Bill B | Business Users Application Checkout
56 | 2022-04-30 18:00 |  | 2022-04-30 18:00 | [5 empty] | Milestone: Applications Verification Complete
58 | 2022-04-30 18:00 |  | 2022-04-30 18:00 | [5 empty] | Wait for external systems restart and verification
60 | 2022-04-30 18:00 |  | 2022-04-30 18:00 | [5 empty] | Milestone: Open system for external use, Go Live Complete
Post Go Live Tasks
62 | 2022-04-30 18:00 | 0:30 | 2022-04-30 18:30 |  |  |  |  | James H | Close down Go Live Vitual Room and Phone Conference
64 | 2022-04-30 18:30 | 0:15 | 2022-04-30 18:45 | [5 empty] | Notify business user community that system is available
Formulas:
Start Date Time = IF(ISBLANK([End Date Time, row above]),[End Date Time, row above],[End Date Time, row above])
End Date Time = [Start Date Time]+[Duration]
End Date Time = [Start Date Time]

## Contacts List
First Name | Last Name | Company | Role | Time Zone | Phone | Email | Escalation Contact
Caleb | Jones |  | Data Migration | CST | (999) 111-2222 | caleb.j@mail.com | Jane Doe
Jane | Doe |  | System Engineer | PST | (999) 222-2222 | jane.d@mail.com | James Hoskins
James | Hoskins |  | PM | MTN | (999) 333-2222 | james.h@mail.com | Clay Stands
Clay | Stands |  | Exec Sponsor | MTN | (999) 444-2222 | clay.s@mail.com

## Milestone Comms
Name | Email | Email Distribution Concatenation
Jane Apple | jane.apple@mailbox.com
John Brown | john.brown@mailbox.com | jane.apple@mailbox.com; john.brown@mailbox.com
Clay Charles | clay.charles@mailbox.com | jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com
Shannon Doe | shannon.doe@mailbox.com | jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ; ; ; ; ;
jane.apple@mailbox.com; john.brown@mailbox.com; clay.charles@mailbox.com; shannon.doe@mailbox.com; ; ; ; ; ; ; ; ; ; ; ; ; ; ; ;
| The Full List for copying into email TO field: | {copy above formula, paste as values here}

## App Checkout Issues
App Checkout Issue Log
ID | Capture Date | Identified by | Description | Function | Owner | Status | Comments / Updates
1
2
3
4
5
6
7
8
9
10
11
12

## Rollback Plan
| Planned |  |  | Actual
Task Nbr | Start Date Time | Duration | End Date Time | Start Date Time | Duration | End Date Time | Responsibility | Activity | Comments
Communications for milestones are to be communicated to the list on the "Milestone Comms" tab, unless otherwise noted.
WARNING - This is the Rollback Plan It is to be used only if: {conditions for rollback} Rollback should only occur with agreement of: {names of stakeholders / steering committee}
All times are in US Central time zone
| 2022-06-01 17:00 | [6 empty] | {{ Start Date-Time Place Holder }}
Rollback Scenario 1: to be used when {list conditions}
| 2022-06-01 17:00 | 0:15 | 2022-06-01 17:15 |  |  |  | Last, First | First task
| 2022-06-01 17:00 | 0:15 | 2022-06-01 17:15 |  |  |  | Last, First | Tasks that can be done simultaneously can be given the same start date-time
| 2022-06-01 17:15 | 0:30 | 2022-06-01 17:45 |  |  |  | Last, First | Tasks that must be completed in order should have a start date-time equal to precedent task completion date-time. Note the use of MAX function in Start Date Time to account for the later of planned or actual end date-time
| 2022-06-01 17:15 | 0:05 | 2022-06-01 17:20 |  |  |  | Last, First | Can run concurrent with above row
| 2022-06-01 17:45 | 1:00 | 2022-06-01 18:45 |  |  |  | Last, First | Note use of MAX function in Start Date Time to wait for more than one precedent task to complete
| 2022-06-01 18:45 |  | 2022-06-01 18:45 |  |  |  | Last, First | Milestone: First milestone reached
| 2022-06-01 18:45 | 2:15 | 2022-06-01 21:00 |  |  |  | Last, First | Another task
| 2022-06-01 21:00 | [5 empty] | Last, First | Milestone: Rollback tasks completed
Rollback Scenario 2: to be used when {list conditions}
| 2022-06-01 17:00 | 0:15 | 2022-06-01 17:15 |  |  |  | Last, First
| 2022-06-01 17:15 | 0:15 | 2022-06-01 17:30 |  |  |  | Last, First
| 2022-06-01 17:30 | 0:30 | 2022-06-01 18:00 |  |  |  | Last, First
| 2022-06-01 17:30 | 0:05 | 2022-06-01 17:35 |  |  |  | Last, First
| 2022-06-01 18:00 | 1:00 | 2022-06-01 19:00 |  |  |  | Last, First
| 2022-06-01 19:00 |  | 2022-06-01 19:00 |  |  |  | Last, First | Milestone: First milestone reached
| 2022-06-01 19:00 | 2:15 | 2022-06-01 21:15 |  |  |  | Last, First | Another task
| 2022-06-01 21:15 | [5 empty] | Last, First | Milestone: Rollback tasks completed
Formulas:
Start Date Time = MAX([End Date Time, row above],[End Date Time, row above])
Start Date Time = MAX(D12,G12,[End Date Time, row above],[End Date Time, row above])
End Date Time = [Start Date Time]+[Duration]
End Date Time = [Start Date Time]

## Author Instructions
Go Live Plan Development Process
1 | Work with affected groups to develop a general outline and order of tasks that must be completed for the cutover
2 | Each person/group responsible for a task needs to provide the expected duration to complete the task
3 | Review plan with all affected groups (there is a sample task on the Cutover Plan tab for this)
4 | If needed, obtain approval/sign off from client and/or user groups
General Excel Workbook
1 | Any specific instructions on the use or storage of this workbook
Instructions & Notes Tab
This tab contains information and instructions for those that will be involved in the cutover itself
1 | Update participant instructions as needed
2 | Fill in Virtual Room and Phone Conference Info
2 | Fill in Reference Info as applicable
Timeline
This tab is the step-by-step, minute-by-minute set of tasks to be completed
1 | Fill in the cutover start date & time in cell B6
 Cell B6 is the cutover start date & time. Many formulas key off this cell, which is named StartDT
 Planned Start Date Time for each task is setup to start at the latest of Planned Completion Date Time and Actual Completion Date Time of previous task, so the Planned Start Date Time for upcoming tasks self-adjusts as you fill in Actual Completion Date Time of predecessor tasks
2 | Create tasks, using formulas for Start Date Time and End Date Time, per the included examples
 Adjust the Start date Time formula or even enter a specific value as needed for your specific plan
 Task durations should be gathered from person performing the task (Responsibility)
Rollback Plan
This tab is the step-by-step, minute-by-minute set of tasks to be completed, if needed to rollback application function to source
1 | Fill in the rollback start date & time in cell B8.
 Cell B8 is the cutover start date & time. Many formulas key off this cell, which is named StartDT
 Since this is a Rollback Plan, you won't know ahead of time the actual Start Date Time... just fill in a reasonable date and time
 Should a rollback become necessary, fill in cell B8 with the actual start date and time of the rollback
 Planned Start Date Time for each task is setup to start at the latest of Planned Completion Date Time and Actual Completion Date Time of previous task, so the Planned Start Date Time for upcoming tasks self-adjusts as you fill in Actual Completion Date Time of precedent tasks
2 | Create tasks, using formulas for Start Date Time and End Date Time, per the included examples
 Adjust the Start date Time formula or even enter a specific value as needed for your specific plan
 Task durations should be gathered from person performing the task (Responsibility)
Things to consider...
 In your Go Live and Rollback Plans, include tasks for key communications to all affected groups
 Include a review of the Go Live Plan in your plan (Pre Cutover Tasks)
 Include a "day of Go Live" roll call to ensure all personnel with task responsibility are ready
 All tasks that must be completed a specific number of days before cutover begins should be included in Pre Deployment Tasks
 Include a "no rollback" milestone in the Go Live timeline, beyond which a rollback will not be feasible
 Include all verfication and acceptance tasks in Go Live timeline
 Use Escalation Contact on Contacts List as needed when a task is running long
 Do not skip creating a Rollback Plan, thinking it will just be "reverse the cutover plan"
 You will likely have different Rollback Plans / Scenarios, depending on where in the Go Live Plan that the process breaks down

## Data Validation
Task Status
Complete
In Progress
Issue
Waiting
Not Needed